## Slide 1
From Site to Hearing Room:
Using AI Across the Construction Dispute Lifecycle
Yusuf Kaya, MCIArb
Contracts Director - IC ICTAS (T2IC)
June 11, 2026 • Istanbul
4th ANNUAL
CONSTRUCTION
LAW CONFERENCE
01
Notes: Good afternoon, everyone. My name is Yusuf Kaya. Today I would like to speak about a very practical question: how can the information created during construction be turned into a reliable claim, and eventually into persuasive evidence in a hearing room? AI is a major part of this story. Not because it is a magic button, and not because it replaces professional judgment, but because it can connect and accelerate a process that has traditionally been slow, fragmented and retrospective. My core point is simple: if we want better claims and better dispute outcomes, we have to start much earlier than arbitration. We have to start on site.

## Slide 2
CORE THESIS
The dispute is already forming during construction
AI matters because it can read early signals — but the project must first capture them.
Delayed payments
cash stress • suspension pressure
Scope changes
variation • valuation disputes
Acceleration pressure
productivity • disruption evidence
Design revisions
critical path • causation issues
Material shortages
procurement • price escalation
Financing problems
priority decisions • disruption
Successful project management now includes managing the project under dispute pressure.
SCL Türkiye • 4th Annual Construction Law Conference • Istanbul • 11 June 2026
02
Notes: Let me start with the practical reality of mega projects. A dispute does not suddenly appear when a request for arbitration is filed. It is already forming during construction, while the project team is trying to solve daily technical problems. A delayed payment is not only a financial issue. It may become a programme risk, a suspension risk and later a disruption claim. A design revision is not only an engineering matter. It may become a causation issue in a delay claim. A material shortage is not only a procurement problem. It may become a price escalation or mitigation dispute. This is where AI and new technical methods matter. They help the project team read the signals earlier. But the signal has to exist in a reliable form. If the project has not captured the facts, AI has nothing useful to connect.

## Slide 3
PROBLEM
Construction projects are data-rich but evidence-poor
The issue is rarely absence of information. It is that information is late, fragmented or not claim-ready.
Too much data
Too little structure
Too late analysis
Too weak traceability
The challenge is not collecting more information.
The challenge is turning it into claim-ready evidence.
Data becomes evidence only when it is structured, contextual, traceable and capable of being explained.
The question is not “do we have documents?” It is “can we prove the issue clearly?”
SCL Türkiye • 4th Annual Construction Law Conference • Istanbul • 11 June 2026
03
Notes: This is the real problem in many construction disputes. The project is not empty. The project is full of information. There are daily reports, photos, RFIs, NCRs, minutes of meeting, payment records, progress reports, supplier emails, procurement files and programme updates. But they sit in different systems, different departments, different languages and different formats. So when a dispute starts, the question is not simply: do we have documents? The real question is: can we prove the issue clearly, contemporaneously and in a way that a tribunal can follow? AI is powerful here because it can search, classify, compare and connect massive volumes of information. But its output is only useful if the underlying record is organised and traceable.

## Slide 4
FRAMEWORK
From Site to Hearing Room
The same facts travel through five stages.
1
Capture
site signals
2
Structure
project data
3
Connect
contract issues
4
Analyse
impact & claims
5
Present
hearing evidence
A claim is built every day on site — through records, notices, data and discipline.
SCL Türkiye • 4th Annual Construction Law Conference • Istanbul • 11 June 2026
04
Notes: I will use a five-stage framework. First, we capture site signals. Second, we structure project data. Third, we connect the facts to contractual issues and notice obligations. Fourth, we analyse impact and build the claim. And finally, we present the evidence in the hearing room. The important point is that AI has a role at each stage, but the role changes as the dispute matures. At the beginning it helps capture and classify facts. Later it helps analyse patterns, test claims and prepare the hearing record.

## Slide 5
STAGE 1 • CAPTURE
Capture the record while it is still alive: New methods in the construction phase
The best claim evidence is created while the facts are still fresh.
Mobile daily reports and structured site diaries
Smart watches, badges and access systems for workforce signals
Drones, 360 cameras and photo logs with metadata
IoT, equipment logs, QR codes and RFID tracking
AI-assisted tagging as records are created
Why it matters
The more contemporaneous the record, the less argumentative the later claim becomes.
AI can only analyse what the project has captured.
SCL Türkiye • 4th Annual Construction Law Conference • Istanbul • 11 June 2026
05
Notes: Stage one is capture. The best evidence is usually created when the facts are still fresh. In many disputes, the problem is not that nobody knew what happened. The problem is that the project did not record it in a way that could later support a claim. Daily reports are too general. Photos are not linked to a location or activity. Manpower data is separated from productivity data. Instructions sit in emails, while programme updates sit somewhere else. Modern methods help at the source. Mobile field apps can standardise daily reports. Smart watches, badges and access systems can create workforce presence signals. Drones, 360 cameras and photo logs can preserve visual progress history. IoT and equipment logs can show utilisation and downtime. QR and RFID systems can trace materials and equipment. Then AI can classify and connect those records as they are created. The more contemporaneous the record, the less argumentative the later claim becomes.

## Slide 6
STAGE 2 • STRUCTURE
Turn raw records into project intelligence
Power BI and structured systems make risk visible before it becomes a dispute narrative.
Common data environment
Metadata and taxonomy
BIM / digital twins
Power BI - similar dashboards
Schedule analytics
Knowledge graphs
Dashboards show the pattern. AI explains connections. People decide.
SCL Türkiye • 4th Annual Construction Law Conference • Istanbul • 11 June 2026
06
Notes: Stage two is structure. A project can generate millions of records, but data is not evidence simply because it exists. It needs organisation. This is where common data environments, metadata, taxonomy, BIM, digital twins and Power BI-style dashboards become important. They do not decide entitlement. But they make the project’s risk signals visible and traceable. A dashboard can show progress curves, manpower trends, equipment utilisation, overdue approvals, procurement delays, design revisions and payment status. It can also show whether evidence packs are complete or whether a notice deadline is approaching. AI becomes much stronger when this structure exists. It can search and summarise, but more importantly it can connect related items: a late approval, a programme activity, an email chain, a daily report and a cost record. Dashboards show the pattern. AI explains connections. People decide.

## Slide 7
STAGE 3 • CONNECT
Preserve rights before they are lost
In construction claims, being right is not enough if the contractual clock has already expired.
1
Trigger
design change
late approval
access • payment
2
Clock
clause
deadline
form of notice
3
Draft
notice language
factual basis
reservation
4
Pack
source documents
evidence log
programme extract
Many rights are lost not because the party is wrong — but because the party is late.
AI identifies the window, proposes the action and assembles the pack.
The team decides the strategy.
SCL Türkiye • 4th Annual Construction Law Conference • Istanbul • 11 June 2026
07
Notes: Stage three is connection, and the most immediate example is notices. Many rights are lost not because the party is wrong, but because the party is late. The event may be legitimate. The impact may be real. The cost may be real. But if the notice is late or unsupported, the claim becomes much more difficult. AI-assisted early warning is one of the most practical use cases. The system can watch for triggers: design revisions, late approvals, access restrictions, payment default, repeated disruption, delayed materials or changes in scope. Once a trigger is detected, it can map the event to the clause, identify the contractual clock, help prepare a draft notice and assemble the evidence pack. This does not mean notices should be sent automatically. That would be dangerous. AI identifies the window, proposes the action and assembles the pack. The team decides the strategy.

## Slide 8
ANALYSE
A strong claim is a disciplined evidential chain
AI and dashboards are valuable when they test the chain, not when they merely generate text.
1
Event
what happened?
2
Entitlement
which clause or principle?
3
Causation
how did it affect the works?
4
Quantum
how is the loss calculated?
5
Evidence
what proves each link?
AI-assisted testing
missing evidence • inconsistent correspondence
Expert discipline
causation bridge • programme logic
Commercial strategy
legal risk • final narrative
The objective is not to create a larger claim. It is to create a claim that can be tested.
SCL Türkiye • 4th Annual Construction Law Conference • Istanbul • 11 June 2026
08
Notes: A strong claim is not just a long document. It is a disciplined evidential architecture. There are five links. First, the event: what happened? Second, entitlement: what clause, instruction or legal principle gives the right? Third, causation: how did the event affect the works? Fourth, quantum: how is the loss calculated? Fifth, evidence: what proves each link? In practice, claims often look strong at the beginning but become weak in the middle. The event is clear. The contract clause is clear. But causation is not demonstrated, or the quantum model is not properly connected to source documents. This is where AI can help. It can test the chain. It can ask where the source document is for a number, whether correspondence contradicts the position, whether the event is connected to the programme activity, or whether the evidence is missing. But AI should not replace professional judgment. It should challenge and strengthen the claim before the other side challenges it.

## Slide 9
ANALYSE: DELAY AND DISRUPTION
Delay evidence must be created while the event is happening
Retrospective storytelling is not a substitute for critical path evidence.
event-to-activity mapping
critical path and float alerts
concurrent delay indicators
mitigation decisions recorded contemporaneously
productivity evidence linked to work-fronts
AI-enabled workflow
Event
Programme update
Impact check
Evidence pack
Decision
Delay claim is not prepared in arbitration; it is prepared on site.
SCL Türkiye • 4th Annual Construction Law Conference • Istanbul • 11 June 2026
09
Notes: This is one of the most important parts of the presentation. Delay claim is not prepared in arbitration. It is prepared on site. In construction disputes, delay is often the central battleground. But many teams approach delay backwards. The event happens. The project tries to recover. Years later, when arbitration starts, the delay expert is brought in and asked to reconstruct the critical path impact. The tribunal will ask practical questions. Was the critical path actually affected? Was float consumed? Was there concurrent delay? Were mitigation options available? Was productivity loss recorded? These questions are much easier to answer if the project was monitoring the event while it was happening. AI and schedule analytics can help map events to activities, monitor critical path movement, flag float consumption, identify concurrent delay signals and link productivity records to work-fronts. The point is not that AI performs the expert analysis. The point is that AI helps create a better record for the expert to analyse.

## Slide 10
PRESENT: HEARING PREPARATION
At hearing, data must become a credible human story
AI can help organise the record; advocacy still belongs to professionals.
Chronology
one timeline
Issue map
facts linked to clauses
Witness packs
memory trail
Expert narrative
technical logic
E-bundles
source-linked record
AI contribution
cluster events • find contradictions • prepare first-pass summaries • link exhibits to issues • compare witness accounts against documents
AI can help prepare the room. It cannot read the room.
SCL Türkiye • 4th Annual Construction Law Conference • Istanbul • 11 June 2026
11
Notes: The hearing room is the end of the data journey. By this stage, the question is not whether we have a lot of data. The question is whether the data tells a clear and credible story. AI can help build chronologies. It can prepare issue maps. It can identify contradictions. It can create first-pass witness packs and expert bundles. It can help the team link exhibits to allegations and allegations to source documents. But persuasion remains human. The judgment about what matters, what should be conceded, what should be pressed and how the tribunal is reacting cannot be outsourced. AI can help prepare the room. It cannot read the room.

## Slide 11
GOVERNANCE
Make AI outputs usable in a dispute
The value of AI depends on source links, version control, confidentiality and human approval.
Traceability
Confidentiality
Privilege
Human approval
Audit trail
Quality control
AI is not risk itself. The risk is powerful AI used without professional discipline.
SCL Türkiye • 4th Annual Construction Law Conference • Istanbul • 11 June 2026
12
Notes: Because this is a dispute context, governance is not optional. Every AI output must be traceable to source documents. Confidential project, supplier and legal data must be protected. Privilege must be managed carefully, especially where legal strategy and project records are both being processed. There must be human approval. There must be an audit trail. And outputs must be tested against adverse documents and expert logic. The risk is not AI itself. The risk is powerful AI used without professional discipline. If you cannot prove where an AI output came from, you should not put it into the dispute record.

## Slide 12
ROADMAP
A practical implementation roadmap
Do not start with a big transformation. Start with defensible use cases.
0–30 days
Map high-risk contractual triggers
Identify key data sources
Set confidentiality rules
31–60 days
Build notice and event alerts
Create document taxonomy
Pilot chronology generation
61–100 days
Integrate with claims workflow
Run delay-impact evidence packs
Adopt human approval protocol
Start small. Build trust. Scale only what improves evidence and decision-making.
SCL Türkiye • 4th Annual Construction Law Conference • Istanbul • 11 June 2026
13
Notes: So how do you actually start? My practical answer is: do not start with a big AI transformation. That often creates expensive tools, low adoption and governance risk. Start with defensible use cases. In the first 30 days, map the contractual triggers that create the highest risk, identify the key data sources and set confidentiality rules. In the next 30 days, build notice and event alerts, create a document taxonomy and pilot chronology generation. By day 100, integrate the system with the claims workflow, run delay-impact evidence packs on real events and adopt a human approval protocol. Start small. Build trust. Scale only what improves evidence and decision-making.

## Slide 13
AI will not replace experts.
But experts using AI will replace others.
The future belongs to professionals who combine
technical judgment, legal discipline and data literacy.
Thank you
SCL Türkiye • 4th Annual Construction Law Conference • Istanbul • 11 June 2026
14
Notes: I want to close with the sentence that summarises this whole presentation. AI will not replace experts. But experts using AI will replace others. This is not a distant prediction. In construction, this change is already happening. The professionals who can combine technical judgment, legal discipline and data literacy will identify risks earlier, preserve rights better, prepare more coherent claims and present evidence more persuasively. The future is not a choice between AI and professionals. The future is AI-enabled professionals applying better judgment with better information. Thank you very much.