## Slide 1
Regional Crises and Contractual Obligations
Alp Özzeybek
Partner, Kabine Law
June 11, 2026 - Istanbul

## Slide 2: Regional Crises
Crises in the region in recent times
  Conflict in Ukraine, escalated since Feb 2022
  Conflict in Iran, commenced in Feb 2026
Impact on construction projects in the broader region
  Impact at the site, impact to supply chains
  Time impact, cost impact

## Slide 3: Impact on Contractual Obligations
Force majeure
Hardship
«Price adjustment» provisions
«Change in legislation» provisions

## Slide 4: Force Majeure
Art. 136 of the Turkish Code of Obligations / Art. 119 of Swiss Code of Obligations
      An obligation is deemed extinguished where its performance is made impossible by circumstances not attributable to the obligor.
Turkish Court of Cassation Gen Assembly (YHGK, E. 2017/90 K. 2018/1259)
      Force majeure is an extraordinary event that occurs outside the scope of the responsible party's or debtor's activities and operations, which absolutely and inevitably leads to a breach of a general behavioral norm or an obligation, and which is unforeseeable and unavoidable [...]. Natural disasters such as earthquakes, floods, fires, and epidemics are considered force majeure.
FIDIC Rainbow Suite Clause 18 «Exceptional Events»
      If a Party is or will be prevented from performing any obligations under the Contract due to an Exceptional Event…

## Slide 5: Hardship
Art. 138 of Turkish Code of Obligations (also see Art. 480 for lump sum construction contracts)
    If an extraordinary situation, unforeseen and unforeseeable by the parties at the time the contract was made, arises for a reason not attributable to the debtor, and this situation alters the facts existing at the time the contract was made to such an extent that demanding performance from the debtor would be contrary to the rules of good faith, and the debtor has not yet performed his obligation or has performed it while reserving his rights arising from the excessive difficulty of performance, the debtor has the right to request the court to adapt the contract to the new conditions, or, if this is not possible, to terminate the contract.
Art. 1195 of French Civil Code
    If an unforeseen change in circumstances at the time the contract was entered into renders performance excessively onerous for a party who did not agree to assume the risk, that party may request renegotiation of the contract from its counterparty. […] If no agreement is reached within a reasonable time, the court may, at the request of a party, revise the contract or terminate it, on the date and under the conditions it determines.
FIDIC Contracts guidance on the effects of inflation and unavailability of goods and labour following the global COVID-19 pandemic and the war in Ukraine (March 2023):
    Where the Contract does not provide for compensation for full inflation Cost, … remedies may exist at law. This is the case in some civil law countries, … where the so-called “hardship theory” may provide for specific remedies in such a situation.

## Slide 6: «Price Adjustment» provisions
FIDIC Yellow Book 2017 Sub-clause 13.7
If the amounts payable to the Contractor are to be adjusted for rises or falls in the cost of labour, Goods and other inputs to the Works, for this Sub-Clause to apply it is important that a Schedule (or Schedules) of cost indexation is (are) included in the Contract and that such Schedule(s) include a formula or formulae for calculation of the applicable adjustment under this Sub-Clause.

## Slide 7: «Change in Legislation» provisions
FIDIC Yellow Book 2017 Sub-clause 13.6
    Subject to the following provisions of this Sub-Clause, the Contract Price shall be adjusted to take account of any increase or decrease in Cost resulting from a change in:
      (a) the Laws of the Country (including the introduction of new Laws and the repeal or modification of existing Laws);
      (b) the judicial or official governmental interpretation or implementation of the Laws referred to in sub-paragraph (a) above;
      (c) any permit, permission, license or approval obtained by the Employer or the Contractor under sub-paragraph (a) or (b), respectively, of Sub-Clause 1.13 [Compliance with Laws]; or
      (d) the requirements for any permit, permission, licence and/or approval to be obtained by the Contractor under sub-paragraph (b) of
    Sub-Clause 1.13 [Compliance with Laws], made and/or officially published after the Base Date, which affect the Contractor in the performance of obligations under the Contract. In this Sub-Clause “change in Laws” means any of the changes under sub-paragraphs (a), (b), (c) and/or (d) above