## Slide 1
Towards a Better Understanding: Delay Analysis Methodologies Revisited
A Contractor’s Perspective
Paul Taggart
Webuild

## Slide 2: The Perception
Rocket science?
Blackbox?
Technobabble?
Gobbledygook!
Many titles?
Recognisable
universal language and rules … well almost ! …
for technical and legal professionals.

## Slide 3: Main Methodologies
Impacted as planned.
  Primitive,
  usually of little practical use … limited demonstration of cause and effect,
  typically, poor claim outcome resultant,
  minimal contractual and legal support.
Time impact analysis.
  The weapon of choice … applicable during the currency of the project,
  useful if tempered with common sense (and not ideology) leading to sensible outcomes,
  better contractual support (prospective approach of many forms),
  typically, unattractive to CA’s (EOT entitlement is typically ignored).
As Planned versus As Built.
  the last resort,
  too often adopted due to the absence of poor contract administration and scheduling habits,
  can be harsh by ignoring the realities and difficulties of performing works.

## Slide 4: Why a Delay Analysis is Pertinent
Functionally: Acts as both a sword and a shield with respect to liquidated damages and recovery of delay costs.
Financially: A professionally (and independently) compiled delay analysis adds value (real $$$ usually).
Practically: The result can give some certainty and sense of reality from a working programme perspective. It can then give the basis for an agreement of a proper construction programme … an act of de-escalation allowing focus on delivery.
Strategically: It gives back control of the execution programme.
Operationally: Preservation of time and control of the delivery programme i.e., obtaining adequate time to do the job in an orderly and economic manner. Management of subcontractors and interfaces.
Disputes: Investment to prevent money being spent on costly disputes in the long term … (TIA) is better than cure (APAB)?

## Slide 5: The Key Issues
Choice of delay analysis methodology
Many to choose from but only few are relevant. Chose appropriately if you want the desired outcome … glass half empty is usually a glass half empty in this case.
Choice of Expert
Internal resources versus external resources?
Gravitas. In the case of DB’s and Arbitral work, the character, and experience (authority) of your expert counts. In the case of arbitration don’t be afraid to interview for your own satisfaction.
Content: Simplistic presentations and conclusions are essential!
By all means produce the detailed analytical report but remember that it has to be understood by the counterparty, by the DB, or an Arbitral tribunal if it is to succeed.
Arbitrators will typically receive two reports with very different outcomes and opinions. Who do they believe. They will want a simple a credible representation of the facts and its likely that’s all they can understand, relying on the authority and credibility of the deliverer.

## Slide 6
Thank YOU!

## Slide 7
A Contractor’s Prespective
Paul Taggart
CCS LLP