## Slide 1: Constructive Acceleration: Exploring the delay/accelerate quandary
Robert D’Onofrio, Capital Project Management, Inc
Professor Doug Jones AO
Kim Rosenberg, Freshfields
Moderated by Dr Hamish Lal

## Slide 2
Commercial realities relevant to acceleration
Critical delay = late completion (unless accelerate) = delay costs/losses
  Efficient acceleration is when acceleration costs less than late completion
There is a window for efficient acceleration – otherwise, acceleration becomes inefficient
Imprecise information available to the parties to determine whether proposed acceleration would be efficient
The 9 unbreakable rules of the Wile E. Coyote/Road Runner universe - Vox

## Slide 3
Origins of constructive acceleration doctrine
United States Armed Services Board of Contract Appeals
  Historically, jurisdiction limited to contractual disputes
Led to decisions that, in some circumstances, written instruction not required to instigate a Change
That principle then applied where Contractor deprived of EoT to which it entitled and government insisted on timely performance
Armed Services Board of Contract Appeals (asbca.mil)

## Slide 4
Elements of constructive acceleration in U.S.
Contractor encountered excusable critical delay
Contractor made timely and sufficient request for EoT
Employer denied request or failed to act within reasonable time
Employer insisted on completion within shorter time than Contractor would be entitled given excusable critical delay
Contractor was required (and did) expend extra resources to accelerate
Cartoon Woman Chasing Man Rolling Pin: vetor stock (livre de direitos) 616397687 | Shutterstock

## Slide 5
Industry Standard ANSI/ASCE/CI 67-17 (ASCE 67)
Guideline 11.3: Constructive acceleration may be proved by showing that
The contractor encountered an excusable delay,
the contractor made an appropriate time extension request,
the owner denied all or part of the time extension request or failed to act on it within a reasonable time,
the owner insisted the earlier completion date must be met or insinuated liquidated damages and the contractor notified the owner that the alleged acceleration order was regarded as a constructive change, and
the contractor expended additional costs to accelerate performance

## Slide 6
1. Contractor encountered excusable critical delay
Excusable but not necessarily compensable
Cause of / responsibility for predicate delay may not be known at time acceleration decision is needed
Vector Cartoon Illustration of Two Men or Businessmen Blaming and Pointing at Each Other Stock Vector - Illustration of accusation, shame: 203094627 (dreamstime.com)

## Slide 7
2. Contractor made timely & sufficient EoT request
Submitted notices & claims on time
Content of notices and claims is compliant
Premium Vector | Businessman signing insurance claim form (freepik.com)

## Slide 8
Constructive Acceleration Example
Months
1
2
3
4
5
6
7
8
Required Contract
Completion Date
Path B
Path A
Scheduled
Completion
0 Float
0 Float
0 Float
Scheduled
Completion
-30 Float
-30 Float
0 Float
Path B
Path A
30 day
excusable
delay
30 day excusable delay event
Contractor requests time extension
Owner denies request for time extension
Contract completion date not appropriately adjusted
30 day projected delay
Activity
Critical Activity
As-Built
Owner Delay Contractor Delay
As-Built Critical Path
Source: Dale and D’Onofrio, Construction Schedule Delays (Thomson Reuters 2022), Figure 3-5

## Slide 9
Months
1
2
3
4
5
6
7
8
Required Contract
Completion Date
Path B
Path A
Scheduled
Completion
0 Float
0 Float
0 Float
Owner threatens liquidated damages or insists contract completion date must be met
Contractor accelerates to meet required completion
Owner liable for contractor’s costs
Path B
Path A
Scheduled
Completion
-30 Float
-30 Float
0 Float
Activity
Critical Activity
As-Built
Owner Delay Contractor Delay
As-Built Critical Path
Source: Dale and D’Onofrio, Construction Schedule Delays (Thomson Reuters 2022), Figure 3-6
Constructive Acceleration Example

## Slide 10
Source: Dale and D’Onofrio, Construction Schedule Delays (Thomson Reuters 2022)
Acceptability percentage of schedule delay analysis methods
# of Cases: 91 17 49 38 76
Time Impact Analysis
Method:
Collapsed
As-built
As-built Critical Path
Impacted As-planned
As-planned v. As-built
Chart: 
| Time Impact Analysis | Collapsed As-Built | As-built Critical Path | Impacted As-Planned | As-Planned v As-built
%Accepted | 0.62637 | 0.23529 | 0.16327 | 0.23684 | 0.17105
Study of 271 judicial decisions from the US, UK, Canada, Australia, HK, and Korea

## Slide 11
3. Denial of EoT or failure to timely assess
Consider Contract time periods for assessment of claims (and any deeming provision)
More challenging if Contract does not specify time period
May be relevant if EoT is partially denied only
Employer cannot have impliedly directed acceleration where they were not given opportunity to grant EoT
Premium Vector | Tiny male and female characters with huge pen and seal stamp at denied insurance claim certificate. protection of health, life, real estate and property interests. cartoon people vector illustration (freepik.com)

## Slide 12
4. Employer insisted on scheduled completion
Require threat of liquidated damages
In U.S. federal contracting context, also require contemporaneous notice from Contractor that it considers there to be an instruction for constructive change
Fact specific
Reading Sinners the Riot Act in the Year of Mercy (aleteia.org)

## Slide 13
5. Expending resources to accelerate
Added crews or increased crew sizes
Overtime or shift work
Additional tools and equipment
Additional supervision or jobsite overhead
Expediting engineering for shop drawings/delegated design
Expedited fabrication/material delivery
Labor inefficiency
Worker Cartoon Images - Free Download on Freepik

## Slide 14
Constructive acceleration in other jurisdictions
Breach of contract
  Breach of obligation to award EoT or breach of obligation to ensure Engineer properly discharged certification function
  In causing predicate critical delay, breach of implied obligation to not hinder Contractor’s progress or possibly breach of express term to timely meet certain requirements
  Breach of obligation to perform in good faith (where applicable)
Challenges with these causes of action

## Slide 15
Breach of obligation to award EoT
Is there a relevant obligation on Contractor’s counterparty?
  Engineer is not party to construction contract & may not act for Employer during certification function
  Obligation on Employer to ensure Engineer properly discharges certification function?
  Implied obligation on Employer not to interfere with Engineer’s certification function?

## Slide 16
Breach of obligation not to hinder progress
Acceleration part of mitigation of loss arising out of breach
However, room for mitigation where EoT machinery in contract?
Premium Vector | Aggressive bully kicking toys. cartoon boy breaks toy cubes, unhappy crying girl children abuse behavior, bad manners kids conflict on playground. flat vector illustration isolated on white background (freepik.com)

## Slide 17
Variation
Decision point for Engineer whether to instruct Variation?
Can have a Variation to introduce acceleration measures?
12 Cartoons That Explain Why Innovation Is So Darned Hard | SAP Blogs

## Slide 18
Causation Elements
Some overlap with elements of entitlement
Predicate critical delay was excusable
Extent of that excusable critical delay
Contractor’s plan was reasonable to achieve completion on time but for excusable critical delay
Acceleration measures were implemented
Claimed costs / losses were caused by excusable critical delay
cheezburger.com

## Slide 19
Checklist to help constructive acceleration claim
Prior to accelerating:
Ensure adequate project records are kept & maintained
Ensure compliance with EoT notice & claim requirements
Consider any mitigation obligation
Wait for determination on EoT claims
Give notice of intended acceleration
Seek to agree acceleration methods
Ensure compliance with constructive acceleration notice & claim requirements
What is a Checklist? - Smartpedia - t2informatik

## Slide 20
Checklist to help constructive acceleration claim
During/after acceleration measures:
Maintain progress records
Assess delay recovery and reassess
Maintain separate cost codes & records for acceleration measures
Regularly update Engineer / Employer
The Event Planning Checklist Used By Top Event Planners (wildapricot.com)

## Slide 21
Perspectives of an Arbitral Tribunal

## Slide 22
The importance of a convincing factual case and contemporaneous records