## Slide 1
ECI:
Reducing Risk Before It Is Allocated
Andrew Aglionby
Partner, A&C International Law
June 11, 2026 - Istanbul

## Slide 2
The Central Proposition
ECI changes when risk is understood, priced and allocated.
The issue is not whether risk is transferred, but whether it is understood before it is allocated.
ECI does not remove risk transfer.
It improves the factual basis on which risk is priced and allocated.
The Two Bridges: A Tale of Two Projects
Premature
risk transfer
Investigation
& contractor input
Informed
risk allocation
2

## Slide 3
Roadmap
1
Timing matters more than drafting
Risk allocation may be clear, but still premature, if the underlying risk is not yet understood or controlled.
2
Outcomes improve
ECI narrows the unknown-risk premium by improving the information on which pricing and risk decisions are made.
3
Comparison with EPC and traditional models
ECI is not anti-EPC. It makes later risk transfer more robust by testing design, programme and interface assumptions earlier.
4
Phase 1 payment & IP
Phase 1 is an investment in information. Payment provisions determine its cost; IP provisions determine who may use its value.
3

## Slide 4
1. Timing, Not Softness
ECI’s real innovation is temporal: understand the risk first, allocate it later.
Risk allocation answers one question:
if the risk materialises, who bears it?
In EPC / hard lump-sum structures, price and risk may be fixed before design, ground conditions, interfaces and delivery assumptions are mature. ECI defers final risk transfer until the factual basis is more reliable.
Case analogy
MT Højgaard v E.ON
Takeaway: obligations of this weight should be stress-tested before they are frozen into the delivery contract.
.
4

## Slide 5
2. Pricing the Unknown
Transferred risk is not eliminated; it is priced, qualified or disputed later.
Risk transferred ≠ risk eliminated
When immature risk is transferred wholesale, the contractor has three rational responses:
Price the
worst case
Qualify
it out
Under-price
then claim
ECI narrows the unknown-risk premium
Structured investigation
Practical contractor input
Tested assumptions
Better pricing basis
5

## Slide 6
3. Traditional Employer-Design
Contractor input often arrives after the design has largely been fixed.
Traditional employer-design
Employer design
Tender
Contractor arrives
Variations / disputes
Buildability, sequencing, temporary works, interface and programme risks may be discovered too late.
ECI
Employer concept
Contractor input
Test & mature
Informed allocation
ECI reduces that exposure by testing buildability, programme realism and interface control while the design can still change.
7

## Slide 7
3. Compared With EPC / D&B
ECI is complementary to later risk transfer; it is not mutually exclusive with EPC.
EPC is excellent at packaging risk;
ECI is often better at understanding it.
EPC works well where:
Scope is mature
Technology is established
Interfaces are limited
Delivery conditions are knowable
Where those conditions are absent:
Full transfer may buy contingency pricing, not certainty
Delay, defect and termination disputes become more likely
FIDIC Silver Book guidance cautions against use where risk cannot be assessed
ECI can make any later D&B / EPC allocation more robust.
8

## Slide 8
Reducing Risk for Both Parties
ECI improves information before the parties commit to final risk allocation.
For the employer
Fewer unknowns priced as contingency
Earlier testing of design and programme assumptions
Reduced exposure to variations, EOT and defects disputes
Stronger factual basis for allocation
For the contractor
Fewer obligations accepted on insufficient data
Clearer design and methodology interfaces
More realistic pricing and programme
Less pressure to under-price and claim later
Both sides are protected from committing on an insufficient factual basis.
9

## Slide 9
4. Phase 1 Payment & IP
Phase 1 is the point at which the employer pays for information, not EPC delivery risk.
In Phase 1, the employer pays for information — not EPC delivery risk.
Payment provisions determine the cost of that information.
Design interrogation · methodology · programme testing · supply-chain engagement · risk retirement
Trap 1: non-conversion
If Phase 2 does not proceed, can the employer use the Phase 1 outputs with another contractor?
Trant v Mott MacDonald: access and use rights should be secured at the outset.
Trap 2: IP and data
Usability may matter more than ownership: a paid-up, irrevocable project licence may be the practical approach.
10

## Slide 10
Close
The right contrast is
informed versus premature
risk allocation.
ECI is not merely a procurement preference.
It improves the quality of decisions before the parties commit to a final allocation of risk.
The ambition of ECI is not to make contracts kinder;
it is to make risk transfer more intelligent.
11

## Slide 11
Questions
Thank you.
Andrew Aglionby | A&C International Law
12