## Slide 1: FIDIC 2022 Amendments – What works and what doesn’t?
Adrian Bell
adrian.bell@cms-cmno.com
October 2023

## Slide 2
FIDIC 2022 Amendments – introduction
In 2022, FIDIC released a set of amendments to its 2017 Second Edition (Red, Yellow and Silver)
Updated version of FIDIC Contracts Guide for use with Second Ed. contracts provided at same time
A number of significant points arise from the amendments and guidance
Today’s presentation focuses on those points relating to claims and disputes
Revised definitions of “Claim” and “Dispute”

## Slide 3
Revised definition of “Dispute”
Narrowed in 2 ways:
  Requires an Engineer’s determination process under clause 3.7, including the service of a Notice of Dissatisfaction
  Only “Claims” and clause 3.7 matters are included within the definition of “Dispute”
Has the intention actually been carried through in the drafting of the new definitions?
What purpose is served by excluding certain claims from the ambit of the DRP?

## Slide 4
Difficulties arising from requiring cl. 3.7 process to be carried out
Urgent disputes
Legacy claims
Local law termination or recission
Procedural disputes

## Slide 5
Implied entitlement to bypass cl. 3.7 process?
Certain exceptions where requirement to follow cl. 3.7 process
Cl. 3.7 process is disapplied for disputes over terminations
Other issues

## Slide 6
Other 2022 amendments
Clause 1.5: “conflicts” within contract docs must be notified to Engineer
Change to final payment procedure in clause 14.13
Exceptional Events must now officially be “exceptional”
Sub-clause 17.2(e) has been widened
FIDIC is now the default appointer of DAAB members
Independence criteria for DAAB members has been reduced

## Slide 7
2nd Edition Guide – areas of ambiguity
Second Edition Claims procedure is highly regimented and specific, with many deeming provisions. But could stall around the giving of a “fully detailed Claim”
Time bar only applied to Statement of Legal Basis element and not the rest of the fully detailed claim
Guide explains what process was in fact intended
But Guide fails to address the clear potential to stall the process and allow parties to effectively save up disputes until the end of the project (something which the new claims procedure was intended to avoid …)

## Slide 8
2nd Edition Guide – areas of ambiguity (cont.)
Liability for latent defects was thought to be preserved under the First Edition
Qualified in Second Edition by express limitation period for Plant
Drafting leaves ambiguity – is the word “occurring” intended to apply to both “defects” and “damage”?
Is the word “more” qualified by the word “occurring”?
Guide provides some light on the issue

## Slide 9
Conclusion
New amendments and Guide are in some respects helpful in clarifying minor issues
Overall, they have probably done more harm than good
Likely to increase disputes and need to involve national courts
A further round of amendments seems inevitable